## task to do
Serial no | Task to do | importance | 19-11-2024 | 20-11-2024 | 21-11-2024 | 22-11-2024
1 | Identifiy the joining colums,Validate numeric colum is present before join | 0 | completed (G) | updated the joing code completed(G)
2 | save and retrive AI dashboard | 0 | working on | 1 completed (J)/2nd one working on (J)
3 | check global df is null if all users are logged out or ther is no user | 1 | pending
4 | Check where the global df is saved | 1
5 | global df has to work using in-memory | 2
6 | OLTP AND OLAP | 2
7 | add dashboard filter | 2
8 | add silent login in employeelist and api integration | 1
9 | check red is (catch memmor) can use or not | 3
10 | white labeling | 3
11 | disable backbutton ,only go back to login page after logout only | 1 | working on | first test is completed(J)
12 | excel upload:-(if any chart with perticular table then that table cannot deleted) | 2 | pending
13 | confidential chart | 1
14 | reporting id (manager who can view the charts of specified emp,loyees) | 2
15 | dashboard view filtering accoring to the company | 0 |  | completed (G)/(J integrated)
16 | client db (orgination Db) connection for data load | 2
17 | during Sign Up there is a bug, that need to fix need to fix | 0 | completed (J)
18 | color change for each chart | 1
19 | display the charts and dashboard according to the user id | 1
20 | change colour of bar chart
21 | filtering in join
22 | create dashboard comes in design dashboard , view dashboard

## Sheet5
serial no | module | Test case | test case type | status
1 | charts | Admin login | positive | pass
2 | charts | Admin | negative | Fail
3 | charts | In check box,csv or ex file are clicked and x axis,y axis are shown | positive | passed
4 | charts | x axis and y axis,drag and drop function are checked | positive | passed
5 | charts | fiters are testes | positive | passed
6 | charts | tired bar and pie chart should be displayed | positive | passed
7 | charts | line and area chart are should be displayed | positive | passed
8 | charts | map chart(select country) and should be display | positive | passed
9 | charts |  | positive
10 | charts | SV-chart ,single value x axis tested | positive | passed
11 | charts |  | positive
12 | charts | Tree hierarchy(multiple x axis and no need y axis) ,Hierarchy are tested(need one y axis, and multiple x axis) | positive | passed
13 | charts |  | positive
14 | charts | all charts are tested to be displayed | positive | passed
15 | charts |  | positive
16 | charts | sv chart (count) should be displayed | positive | passed
17 | charts | Try to drag and drop it should be placed correctly | positive | passed
18 | charts | If i give bar chart, it should be displayed properly | positive | passed
19 | charts | If i give all the charts in x axis and y axis, all charts are displayed properly | positive | passed
20 | charts | hierarchy chart,when edit section there will be no colour appear in chart | negative | failed
21 | charts | if i give count in SV chart ,it should display the count properly | positive | passed
22 | charts | if i give two x axis value for hierarchy,it should be displayed | negative | failed
23 | admin | if I give wrong company name,the popup box should be incorret company name like that | negative | failed
24 | admin | In edit part,when I click edit button im facing (uncaught runtime error) | negative | failed
25 | admin | In login page,sometimes the two pages are merging | (merging problem) | (merging problem)
26 | admin | if i gave company user name HONDA, it should be work | positive | passed
27 | admin | if i gave another company name try to login (TATA) it should be open | positive | passed
28 | admin | the company name (suzuki) try to signup,it should be open | positive | passed
29 | admin | Given wrong username,it should be display the popup box isnt not correct | positive | passed
30 | admin | Given wrong password,it should be display the popup box isnt not correct | positive | passed
31 | admin | If i gave wrong company name and correct username and password,it should display the popup msg | positive | passed
32 | admin | If i gave correct company name and wrong username or password, it should displayed the popup box. | positive | passed
33 | admin | When i give correct username and password,it should be open | positive | passed
34 | admin | if i gave another company name and its empolyee crt username and password, it should be open | positive | passed
35 | admin | After that CSV file and excel file uploded | positive | passed
36 | admin | while uploading audio file there was a error shown as (network error) | negative | failed
37 | admin | if i gave different company name and username,password,it should be open | possitive | passed
38 | admin | Try to upload csv or excel file,it should be upload succesfully | positive | passed
39 | Dashboard | when i try to save multiple charts and save to dashboard, it should be saved properly | positive | passed
40 | Dashboard | when i try to multiple diffrent charts on dashboard,it should be displayed properly | positive | passed

## connecting status
Serial No | DATE | ATTANDANCE | No.of task Completed | NOTE | TESTING | connecting duretion
1 | 19-11-2024 | jagath,gayathri | 2 task completed | 2 task are now working on.. |  | 30 min
2 | 20-11-2024 | jagath,gayathri,sanjay | 2 tast completed | 2 task are now working on.. | 3 test cases are done | 45 min

## testing
Testing |  | status
1 (1) | In login page, to check back and front button works,(IT SHOULD NOT BE BACK TO LOGIN PAGE.) | checked
2(1) | when upload a two empolyee data bt different login, the login should be work properly to there respective two data
3(2) | once in chart 1 is drag and drop,whatever charts and dashboard, I want to disable that need to test (ON DIFFEREENT TABLES)
4(2) | if user 1 and user 2 are tcs empolyee,users create(PROJECTS) charts and manager want to see the chart means,we can able to set to see the other user charts in manager login

## testCases
work | Test step | Step action | Step expected | Assigned to | Description
Test case | 1 | user has given access to the respective desktop. Step 1: login into login page. Step2: verify user can view the box ID and password icon in the screen. | User can view box ID capture in UI | sanjay | Verify User can view "sign in" in landing page and once click back its going to login page
Test case | 2 | user has see the dashboard in Data source,Design,Edit,View. Verify the user can able to click . | once click the csv,excel,audio and custom data are viewed.
|  |  |  | sanjay | Verify User can view all the buton are working.
Test case | 3 | In top left corner,the three bar icon has not working
|  |  | once clicked that icon its not detected | sanjay | verify the three bar icon is defeacted
Test case | 4